## Sheet1
Type | Description | Impact | Owner
Risk | Vendor delays network gear shipment | High | Network Lead
Assumption | Cloud resources will be provisioned within 2 days | Medium | Cloud Lead
Issue | Telecom carrier not responding to circuit requests | High | Telecom PM
Dependency | Dependent on finance team for budget release | Medium | Project Manager