## Sheet1
Task ID | Task Name | Start Date | End Date | Status | Owner
1 | Site Selection & Approval | 2025-07-01 | 2025-07-05 | Complete | PMO
2 | Network & Telecom Setup | 2025-07-08 | 2025-07-14 | In Progress | Network Team
3 | Cloud Infrastructure Deployment | 2025-07-15 | 2025-07-21 | Pending | Cloud Team
4 | End-User Device Configuration | 2025-07-22 | 2025-07-28 | Pending | IT Support
5 | Go-Live & Final Testing | 2025-07-29 | 2025-08-02 | Pending | PMO